## Slide 1
2020
2020
Requirements
Development
Reviews
Today
Week 1
3
5
7
9
11
13
15
17
19.6 days
Feb 9 - Feb 28
Requirements
9 days
Estimation
Feb 27 - Mar 6
26 days
Prototype
Feb 27 - Mar 23
10 weeks
Production Development
50%
17.4 days
Deployment
Feasibility Review
Mar 11, 2020
Mid-cycle Review
Apr 16, 2020
Pre-release Review
May 18, 2020
Mar 22 - May 31
May 14 - May 31
Project Approval
Feb 4, 2020
Handoff to Production
May 31, 2020
Use this demo timeline to get acquainted with Swimlanes
Click the Edit Data button to add, remove or change milestones and tasks.
Use the Style Pane to uniquely customize any element on the timeline.
Click Edit Timeline to adjust the layout by dragging & dropping elements.

## Slide 2
2021
2021
Research
Write-up
Planning
Today
Jan
Feb
Mar
Apr
May
Jun
2021
21 days
Jan 29 - Feb 28
Background Study
50%
10 days
Feb 28 - Mar 14
Implementation Phase
11 days
Mar 15 - Mar 29
Write-up Results
12 days
Jan 28 - Feb 12
Finalize Project Plan
100%
4 days
Mar 30 - Apr 4
Incorporate Feedback
Submission before opposition
May 21
Draft peer review
Mar 30
Results peer review
Apr 26
Final submission
Jun 9
Submit Project Specification
Feb 12

## Slide 3
Planning Phase
Research Phase
Write-up Phase
Analysis Phase
Jan
Feb
Mar
Apr
May
Jun
2022
11.5 days
Jan 28 - Feb 12
Finalize project plan
100%
10.5 days
Mar 20 - Mar 29
Write-up: Results
Mar 30 - Apr 4
Incorporate feedback
Jan 28 - Feb 25
Background study
Apr 26 - May 5
Incorporate feedback
Mar 7 - Mar 14
Analysis & isolation of the properties of converging & diverging MKBSC games
Mar 1 - Mar 7
Systematic construction & analysis of Multi-Agent games
Apr 4 - Apr 25
Write-up: Discussion
Mar 15 - Mar 20
Write-up: Method
Feb 25 - Feb 28
Study of MKBSC toolkit
May 11 - May 14
Final incorporation of feedback
Deadline: Project specification
Feb 25
Peer review of inital draft
Mar 30
Peer review of findings
Apr 26
Deadline: Report draft for opposition
May 21
Deadline: Final submission
Jun 9
Supervisor Meeting: Background
Feb 25
Supervisor Meeting: Results
Apr 5
Deadline: Email Report draft to supervisor
May 7
Supervisor Meeting: Final comments
May 10
Deadline: Peer Review
May 26

## Slide 4
2020
2020
Today
Week 1
3
5
7
9
2020
11
13
15
17
19.6 days
Feb 9 - Feb 28
Requirements
9 days
Feb 27 - Mar 6
Estimation
17.4 days
May 14 - May 31
Deployment
26 days
Feb 27 - Mar 23
Prototype
10 weeks
Mar 22 - May 31
50%
Production Development
Project Approval
Feb 4, 2020
Feasibility Review
Mar 11, 2020
Mid-cycle Review
Apr 16, 2020
Handoff to Production
May 31, 2020
Click the Edit Data button to add, remove or change milestones and tasks.
Use the Style Pane to uniquely customize any element on the timeline.
Click Edit Timeline to adjust the layout by dragging & dropping elements.
Use this demo timeline to get acquainted or click New in the Office Timeline ribbon to build your own